## Project Timeline
Probe Agile Frontend Develpoment Schedule
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in person days | DURATION in hours | COMMENTS
| Task 1 - Probe Agile Data Landing page development creating metric report for last 7 days |  | In Progress | Prem kumar | 2023-11-30 | 2023-12-01 | 1 | 9
| Subtask 1.1 | log detalils of fema,startup india development and accessing data from database functionalities in popup window. | In Progress | Prem kumar | 2023-12-01 | 2023-12-02 | 1 | 9
| Task 2 - Navigating page for fema table results development and accessing data from database |  | In Progress | Prem kumar | 2023-12-04 | 2023-12-05 | 1 | 9
| Subtask 2.1 | creating date range filtering options for fema table results that is historic data results | done | Prem kumar | 2023-12-05 | 2023-12-06 | 1 | 9
| Task 3- Navigating page for startup india table results development and accessing data from database |  | Not Started | Prem kumar | 2023-12-06 | 2023-12-07 | 1 | 9
| Subtask 3.1 | creating date range filtering options for startup india table results that is historic data results | Not Started | Prem kumar / mohan | 2023-12-07 | 2023-12-08 | 1 | 14
| Task 4- final testing |  | Not Started | Surya / Prem kumar | 2023-12-08 | 2023-12-09 | 1 | 14
| Task 5 - Deployment |  | Not Started | Surya | 2023-12-11 | 2023-12-12 | 1 | 9
[6 empty] | Total | 8 | 82

## Project Timeline - BLANK
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*