## IRDA
IRDAI Schedule
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| IRDAI |  | Medium
| Subtask 1.1 | Analysis |  | Completed | Udhaya Kumar & Bhuvana | 2024-04-17 | 2024-04-17 | 1 | 8
| Subtask 1.2 | DB Setup |  | Completed | Bhuvana | 2024-04-22 | 2024-04-22 | 1 | 8
| Subtask 1.3 | Scripting |  | In Progerss | Bhuvana & Udhaya Kumar | 2024-04-23 | 2024-04-26 | 4 | 32 |  | Historical Script - In Progress Incremental Script - Not Started Log Table - Not Started
| Subtask 1.4 | Script-Testing with bulk data extraction |  | Not Started | Bhuvana | 2024-04-29 | 2024-05-02 | 3 | 24
| Subtask 1.5 | API Setup |  | Not Started | Prem kumar & Bhuvana | 2024-05-03 | 2024-05-06 | 2 | 16
| Subtask 1.6 | API Testing |  | Not Started | Udhaya Kumar & Surya | 2024-05-07 | 2024-05-07 | 1 | 8
| Subtask 1.7 | API Documentation |  | Not Started | Udhaya Kumar | 2024-05-08 | 2024-05-08 | 1 | 8
| Subtask 1.8 | E2E Testing |  | Not Started | Prem kumar | 2024-05-09 | 2024-05-09 | 1 | 8
| Subtask 1.9 | Dashboard |  | In Progerss | Prem kumar | 2024-04-23 | 2024-04-26 | 4 | 32 |  | Creating code for dashboard with sample database.
| Subtask 1.10 | Deployment |  | Not Started | Bhuvana | 2024-05-10 | 2024-05-10 | 1 | 8
[7 empty] | Total | 19 | 152

## PFRDA
PFRDA Schedule
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| PFRDA |  | Medium
| Subtask 1.1 | Analysis |  | Completed | Magudapathy & Mohan kumar | 2024-04-17 | 2024-04-17 | 1 | 8
| Subtask 1.2 | DB Setup |  | Completed | Mohan kumar | 2024-04-22 | 2024-04-22 | 1 | 8
| Subtask 1.3 | Scripting |  | In Progerss | Mohan kumar & Magudapathy | 2024-04-23 | 2024-04-24 | 2 | 16 |  | Historical Script - In Progress Incremental Script - Not Started Log Table - Not Started
| Subtask 1.4 | Script-Testing with bulk data extraction |  | Not Started | Magudapathy | 2024-04-25 | 2024-04-26 | 2 | 16
| Subtask 1.5 | API Setup |  | Not Started | Magudapathy & Surya | 2024-04-29 | 2024-04-29 | 1 | 8
| Subtask 1.6 | API Testing |  | Not Started | Mohan Kumar | 2024-05-30 | 2024-05-30 | 1 | 8
| Subtask 1.7 | API Documentation |  | Not Started | Magudapathy | 2024-05-02 | 2024-05-02 | 1 | 8
| Subtask 1.8 | E2E Testing |  | Not Started | Mohan kumar | 2024-05-03 | 2024-05-03 | 1 | 8
| Subtask 1.9 | Dashboard |  | In Progerss | Prem kumar | 2024-04-29 | 2024-05-03 | 4 | 32 |  | Creating code for dashboard with sample database.
| Subtask 1.10 | Deployment |  | Not Started | Bhuvana | 2024-05-06 | 2024-05-06 | 1 | 8
[7 empty] | Total | 15 | 120