## Goverment e Marketplace
Goverment e Marketplace
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | Actual Completed Date | Time Line Met/Not Met | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| Suspended Sellers |  | Simple
| Subtask 1.1 | DB Setup |  | Not Started | MohanKumar | 2024-07-12 | 2024-07-12 |  | Not Met | 0.5 | 5
| Subtask 1.2 | Scripting,Script-Testing with Bulk Data Extraction |  | Not Started | MohanKumar | 2024-07-12 | 2024-07-15 |  | Not Met | 2 | 16 |  | Historical Script - Not Started Incremental Script - Not Started Log Table - Not Started
| Subtask 1.3 | API Setup |  | Not Started | Premkumar | 2024-07-15 | 2024-07-15 |  | Not Met | 1 | 8
| Subtask 1.4 | API Testing & API Documentation |  | Not Started | Surya | 2024-07-16 | 2024-07-16 |  | Not Met | 1 | 8
| Subtask 1.5 | E2E Testing |  | Not Started | MohanKumar | 2024-07-16 | 2024-07-16 |  | Not Met | 0.5 | 4
| Subtask 1.6 | Dashboard |  | Not Started | Premkumar | 2024-07-16 | 2024-07-16 |  | Not Met | 1 | 8
| Subtask 1.7 | Deployment |  | Not Started | Bhuvana | 2024-07-17 | 2024-07-17 |  | Not Met | 0.5 | 3
[7 empty] | Total |  |  | 6.5 | 52

## Resource Loading
Date/Name | Mohan Kumar | Prem Kumar | Surya Selvam | Comments
2024-07-12 | 8
2024-07-15 | 8 | 8
2024-07-16 | 8 | 4 | 8
2024-07-17 |  | 8
Total hours Planned | 24 | 20 | 8
Total hours Available | 24 | 24 | 24
%Utilization | 100% | 83.33% | 33.33%
Comments |  |  | API Testing and Documentation - Since API setup and Testing cannot be done by same resource | Bhuvana will be deploying the source on 17th July
Note on B2: DB Setup and Scripting
Note on B3: Scripting
Note on C3: API Setup
Note on B4: Scripting and API Setup
Note on C4: E2E Testing
Note on D4: API Testing and Documentation
Note on C5: Dashboard