## Source_A
Source A
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | Actual Completed Date | Time Line Met/Not Met | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| Source A |  | Simple
| Subtask 1.2 | DB Setup |  | Not Started | Bhuvana | 2024-06-20 | 2024-06-20 |  | Not Met | 1 | 8
| Subtask 1.3 | Scripting |  | Not Started | Bhuvana & Udhayakumar | 2024-06-21 | 2024-06-24 |  | Not Met | 2 | 16 |  | Historical Script - Not Started Incremental Script - Not Started Log Table - Not Started
| Subtask 1.4 | Script-Testing with Bulk Data Extraction |  | Not Started | Bhuvana | 2024-06-21 | 2024-06-24 |  | Not Met | 2 | 16
| Subtask 1.5 | API Setup |  | Not Started | Udhayakumar | 2024-06-25 | 2024-06-26 |  | Not Met | 2 | 16
| Subtask 1.6 | API Testing |  | Not Started | Magudapathy & Surya | 2024-06-27 | 2024-06-27 |  | Not Met | 1 | 8
| Subtask 1.7 | API Documentation |  | Not Started | Udhaya Kumar | 2024-06-28 | 2024-06-28 |  | Not Met | 1 | 8
| Subtask 1.8 | E2E Testing |  | Not Started | Bhuvana | 2024-07-01 | 2024-07-01 |  | Not Met | 1 | 8
| Subtask 1.9 | Dashboard |  | Not Started | Magudapathy | 2024-06-24 | 2024-06-26 |  | Not Met | 3 | 24
| Subtask 1.10 | Deployment |  | Not Started | Bhuvana | 2024-07-02 | 2024-07-02 |  | Not Met | 1 | 8
[7 empty] | Total |  |  | 14 | 112

## Source_B
Source B
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | Actual Completed Date | Time Line Met/Not Met | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| Source B |  | Simple
| Subtask 1.2 | DB Setup |  | Not Started | Mohan Kumar | 2024-06-20 | 2024-06-20 |  | Not Met | 1 | 8
| Subtask 1.3 | Scripting |  | Not Started | Mohan Kumar | 2024-06-21 | 2024-06-24 |  | Not Met | 2 | 16 |  | Historical Script - Not Started Incremental Script - Not Started Log Table - Not Started
| Subtask 1.4 | Script-Testing with Bulk Data Extraction |  | Not Started | Mohan Kumar | 2024-06-21 | 2024-06-24 |  | Not Met | 2 | 16
| Subtask 1.8 | E2E Testing |  | Not Started | Surya | 2024-06-25 | 2024-06-25 |  | Not Met | 1 | 8
| Subtask 1.9 | Dashboard |  | Not Started | Bhuvana | 2024-06-27 | 2024-07-01 |  | Not Met | 3 | 24
[7 empty] | Total |  |  | 9 | 72

## Bonds and Debentures
Bonds and Debentures
AT RISK | TASK NAME | SUB TASK NAME | COMPLEXITY | STATUS | ASSIGNED TO | START DATE | END DATE | Actual Completed Date | Time Line Met/Not Met | DURATION in person days | DURATION in hours | DEPENDENCIES | COMMENTS
| Bonds and Debentures |  | Medium
| Subtask 1.2 | DB Setup |  | Not Started | Prem Kumar | 2024-06-20 | 2024-06-20 |  | Not Met | 1 | 8
| Subtask 1.3 | Scripting with Script-Testing |  | Not Started | Prem Kumar & Surya | 2024-06-21 | 2024-06-26 |  | Not Met | 4 | 32 |  | Historical Script - Not Started Incremental Script - Not Started Log Table - Not Started
| Subtask 1.4 | Bulk Data Extraction |  | Not Started | Prem Kumar | 2024-06-21 | 2024-07-09 |  | Not Met | 13 | 104
| Subtask 1.5 | API Setup |  | Not Started | MohanKumar | 2024-06-26 | 2024-06-28 |  | Not Met | 3 | 24
| Subtask 1.6 | API Testing |  | Not Started | Magudapathy & Bhuvana | 2024-07-01 | 2024-07-01 |  | Not Met | 1 | 8
| Subtask 1.7 | API Documentation |  | Not Started | Magudapathy | 2024-07-02 | 2024-07-02 |  | Not Met | 1 | 8
| Subtask 1.8 | E2E Testing |  | Not Started | Bhuvana | 2024-07-09 | 2024-07-09 |  | Not Met | 1 | 8
| Subtask 1.10 | Deployment |  | Not Started | MohanKumar | 2024-07-10 | 2024-07-10 |  | Not Met | 1 | 8
[7 empty] | Total |  |  | 25 | 200