## Slide 2
Overall Sources – It’s Status
Source | Development Status | Data Extraction | Maintenance Status | Comments | Source Status
Market data | Completed | Completed | Active |  | 
Start Up India | In progress | In progress | Active | POC completed and shared the observation | 
RBI_ECB | Completed | Completed | Hibernate |  | 
RBI_ODI | Completed | Completed | Hibernate |  | 
MCA_ROC/RD | Completed | Completed | Active |  | 
SEBI | Completed | Completed | Active |  | 
Chairperson / Members |  |  |  |  | 
SEBI_AO | Completed | Completed | Active |  | 
SEBI_Settlement order | Completed | Completed | Active |  | 
SEBI_ED / CGM | Completed | Completed | Active |  | 
Delivery off-track
Delivery at risk
Delivery on track

## Slide 3
Last week Sources And Its Status
Stages of production | MCA _ROC/RD | SEBI | Delivered as per planned schedule? | Comments
Analysis | Completed | Completed | YES | 
DB Setup | Completed | Completed | YES | 
Scripting | Completed | Completed | YES | 
Script-Testing with bulk data extraction | Completed | Completed | YES | 
API Setup/API Testing /API Documentation | Completed | Completed | YES | 
E2E Testing | Completed | Completed | YES | 
Dashboard | Completed | Completed | YES | 
Deployment | Completed | Completed | YES | 
Start-up India Status:
1,00,230 company URLs scrap from the website in 25 days.
We have scraped 6000 company URL’s data in a day using a system.
Totally we scraped 80,000 the data in last 5 days.
Now we are running the script in two system. We will try to run add one more system for scraping the company’s data.

## Slide 4
Issues & Challenges
Market data :
The "SYMBOL not available" error: We're encountering null values in the daily scraping from the ACE company master.
Concerning the unavailability of standalone results: It appears that in the XBRL filings themselves, standalone results are missing. However, some companies have provided consolidated results.
Regarding the "reserves And Surplus Half Year Ending Actuals Currently" field: It was indeed a code base error, and we have fixed it at the code level.
For the "Nature of report is null" issue: This indicates that a particular key is missing in the XBRL filings.
Solutions arrived :
There are 767 companies where the SYMBOL is null.
We are not aware of Related Party Transaction reports. We are not currently processing Related Party Transaction reports. If you would like to include them in our processing, we'll need to develop a mechanism to handle them appropriately. Let me know if you want to proceed with this addition.

## Slide 5
Work Planned for the Week
Source: Import Export Code to be checked in 2 websites as 3 parts.
Status: Team is analysing the complexity of the source.
Working on to automatically capture the Captcha.
The list of PAN details to be shared for the source to calculate the estimation.
Required the list of fields to be stored in the DB table.

## Slide 6
Questions?

## Slide 7
THANK YOU
info@nextwealth.in
www.nextwealth.in